## Sheet1
PROCUREMENT CONTROL REPORT
PROJECT # 1021 |  |  |  | LEGEND: |  |  |  |  | Procept Associates Ltd.
|  |  |  | P | - Planned |  |  |  | Status to:
|  |  |  | F | - Forecast
|  |  |  | A | - Actual |  |  |  | Report #:
- Progress bar
Bid Pkg,.# | Bid Pkg. Description |  | Technical Spec Issued and Approved | PROPOSAL |  |  | Recommendation to Award Issued | Recommendation to Award Approved, P.O. Issued | Architecture Design Received | Architecture Design Approved | WEB Tests Complete | REMARKS
|  |  |  | RFP issued | Proposal Received | Proposal Presentations Complete | [6 empty] | Date:
Duration in Weeks |  |  | 3 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 4
P
F
A
P
F
A
P
F
A
Input Date to the "P" rows. Date Format (dd/mm/yyyy)